## Project schedule
| Europa project | [5 empty] | Project start: | [7 empty] | 2024-11-08
| VanArsdel, Ltd. | Project lead |  |  |  |  | Display week: | [7 empty] | 1
SIMPLE GANTT CHART by Vertex42.com
| https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html | [5 empty] | 2024-11-04 | [6 empty] | 2024-11-11 | [6 empty] | 2024-11-18 | [6 empty] | 2024-11-25 | [6 empty] | 2024-12-02 | [6 empty] | 2024-12-09 | [6 empty] | 2024-12-16 | [6 empty] | 2024-12-23
| TASK | ASSIGNED TO | PROGRESS | START | END | time axis 2024-11-04 to 2024-12-29
 | time axis 2024-11-04 to 2024-12-29
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Initiation
| Define goals | Gokce Aslan | 50% | 2024-11-08 | 2024-11-11 | 4
| Conduct studies | Hayden Cook | 60% | 2024-11-11 | 2024-11-13 | 3
| Establish comms | Jens Martensson | 50% | 2024-11-13 | 2024-11-17 | 5
| Develop charter | Nuria Acevedo | 25% | 2024-11-17 | 2024-11-22 | 6
| Set up team | Olivia Wilson |  | 2024-11-12 | 2024-11-14 | 3
Planning and design
| Create schedule | Gokce Aslan | 50% | 2024-11-13 | 2024-11-17 | 5
| Identify deliverables | Hayden Cook | 50% | 2024-11-15 | 2024-11-20 | 6
| Develop budget | Jens Martensson |  | 2024-11-20 | 2024-11-23 | 4
| Define scope | Nuria Acevedo |  | 2024-11-20 | 2024-11-22 | 3
| Identify risks | Olivia Wilson |  | 2024-11-20 | 2024-11-23 | 4
Execution
| Execute tasks | Gokce Aslan | 50% | 2024-11-23 | 2024-11-28 | 6
| Monitor progress | Hayden Cook | 60% | 2024-11-29 | 2024-12-03 | 5
| Manage resources | Jens Martensson | 50% | 2024-12-04 | 2024-12-09 | 6
| Provide updates | Nuria Acevedo | 25% | 2024-12-10 | 2024-12-14 | 5
| Testing and validation | Olivia Wilson | 25% | 2024-12-04 | 2024-12-08 | 5
Evaluation
| Monitor progress | Gokce Aslan | 25% | 2024-11-25 | 2024-11-28 | 4
| Track expenses | Hayden Cook | 25% | 2024-11-28 | 2024-12-02 | 5
| Evaluate progress | Jens Martensson | 50% | 2024-12-03 | 2024-12-06 | 4
| Address risks | Nuria Acevedo | 60% | 2024-11-30 | 2024-12-03 | 4
| Gather feedback | Olivia Wilson | 50% | 2024-12-02 | 2024-12-07 | 6
Insert new rows ABOVE this one
Formulas:
Display week: = [Display week:, row below]

## About
SIMPLE GANTT CHART by Vertex42.com
About This Template
This template provides a simple way to create a Gantt chart to help visualize and track your project. Simply enter your tasks and start and end dates - no formulas required. The bars in the Gantt chart represent the duration of the task and are displayed using conditional formatting. Insert new tasks by inserting new rows.
Guide for Screen Readers
There are 2 worksheets in this workbook. TimeSheet About The instructions for each worksheet are in the A column starting in cell A1 of each worksheet. They are written with hidden text. Each step guides you through the information in that row. Each subsequent step continues in cell A2, A3, and so on, unless otherwise explicitly directed. For example, instruction text might say "continue to cell A6" for the next step. This hidden text will not print. To remove these instructions from the worksheet, simply delete column A.
Additional Help
Click on the link below to visit vertex42.com and learn more about how to use this template, such as how to calculate days and work days, create task dependencies, change the colors of the bars, add a scroll bar to make it easier to change the display week, extend the date range displayed in the chart, etc.
How to Use the Simple Gantt Chart
More Project Management Templates
Visit Vertex42.com to download other project management templates, including different types of project schedules, Gantt charts, tasks lists, etc.
Project Management Templates
About Vertex42
Vertex42.com provides over 300 professionally designed spreadsheet templates for business, home, and education - most of which are free to download. Their collection includes a variety of calendars, planners, and schedules as well as personal finance spreadsheets for budgeting, debt reduction, and loan amortization.
Businesses will find invoices, time sheets, inventory trackers, financial statements, and project planning templates. Teachers and students will find resources such as class schedules, grade books, and attendance sheets. Organize your family life with meal planners, checklists, and exercise logs. Each template is thoroughly researched, refined, and improved over time through feedback from thousands of users.

## Project Details Planning
Priorotiy Level | Hours Dedicated | Title | Description | Sprint 1 | Hours Completed | AI Made Study Plan | Resources | Subtasks | Sprint 2 | Hours Completed | AI Made Study Plan | Resources | Subtasks

## Scheduling Planner
Task ID | Priority Level | Title | Description | Status | Planned Dedicated Hours | Sprint Start Date | Sprint End Date | Hours Completed | Deliverable | AI Made Study Plan | Resources | Completion Dates
1 | High | Skill Up | Review Software Development Methodologies assignments. Then Build them as a portfolio project | In Progress | 10 | 2024-11-05
1.1 | subtask | Web Scraper | Redo webscraper assignment for S.D.M.
1.2 | subtask | portfolio | Build webscraper for portfolio
1.3 | subtask | Flask ecommerce site | redo flask assignment, or review it
1.4 | subtask | portfolio | build flask ecommerce site for E.O. and add to portfolio
1.5 | subtask | REST API | redo rest api assignment
1.6 | subtask | portfolio | build REST API project for portfolio
2 | High | CS Fundamentals | Review data structures from course and practice coding in python, C# and C and with Leet Code | In Progress | 9
2.1 | subtask | Recap - Python | Python: Vectors, Lists, Object/classes, object life cycle | Completed | [5 empty] | 1. ask AI: what is everything I need to know about lists and numpy as a python developer at microsoft; 2. Ask AI for leetcode problems to practice lists and numpy; 3. ask AI for readings or textbooks to further understanding and check my skills with assesessments. 4. ask ai to quiz me on numpy and lists in python | LeetCode problem 576. Out of Boundary Paths (3 solutions with complexity to compare), Cracking the Coding Interview Chapter 1, Textbook Chapter 1 - 5
2.11 | subsubtask | Leetcode | leetcode problem 576 | In Progress
2.12 | subsubtask | CCI | Cracking Coding Interview: Chapter 1 study | Pending
2.13 | subsubtask | Textbook study | Read textbook and create .py file playing with vectors, Lists, Object/classes, object life cycle. Then use ai to quiz me on content | Pending
2.2 | subtask | Linked Lists |  | Pending
2.3 | subtask | Binary Search Tree
2.4 | subtask | Sorting Algorithms
2.5 | subtask | Priority Queue
2.6 | subtask | Hash Table
2.7 | subtask | Exam 1 and 2
2.8 | subtask | Huffman Encoding
2.9 | subtask | Stacks, Queues, and Graphs
3 | medium | Freelancing |  |  | 8
3.1 | subtask | Prospecting & Job Application
3.2 | subtask | Client Communication & Contract Negotiations
3.3 | subtask | Project Planning & Milestones Setup
3.4 | subtask | Task Execution
3.5 | subtask | Quality Control Review
3.6 | subtask | Project Completion and Payment
3.7 | subtask | Post-Project and Follow-up
4 | low | Open source |  |  | 4
4.1 | subtask | Research and Selection of Open-source project
4.2 | subtask | Environmnet setup
4.3 | subtask | Identify Contribution Opportunities
4.4 | subtask | Task Planning and Timeline Setup
4.5 | subtask | Code Development
4.6 | subtask | Testing and Debugging
4.7 | subtask | Submit Pull Request (PR)
4.8 | subtask | Complete Contribution & Follow-up
4.9 | subtask | Reflect and Track Impact
5 | low | Personal Passion Project |  |  | 5
5.1 | subtask | Planning Phase
5.2 | subtask | Environmnet setup
5.3 | subtask | Backend Development
5.4 | subtask | Frontend Development
5.5 | subtask | Testing Phase
5.6 | subtask | Deployment Phase
5.7 | subtask | Documentation & Portfolio
6 | low | Reading: Clean Code |  |  | 2
6.1 | subtask | section 1
6.2 | subtask | section 2
6.3 | subtask | section 3
7 | low | Advancement | Cloud and AI Research and Instustry Workshops, siminars, papers (how it's being used in products? What does the latest research say?) |  | 2 | [5 empty] | See list of journals & organizations on my website
7.1 | subtask | Cloud Computing
7.2 | subtask | AI and ML
40